# GradUp – Graduation Project Management Plan

DEPI Industry Track | Version v0.1 | 15 October 2026

All dates follow the Primavera schedule window of 2 Oct to 4 Dec 2026.

# Document Control

| Field | Entry |
| --- | --- |
| Project title | GradUp – Digital Incubator & Accelerator for Graduation Projects |
| Team / cohort | ONL5_ERP11_S1 - Even - Google Project Management – DEPI Industry Track |
| Project manager / team lead | Mohamed Rizk (Team leader) |
| Team members | Asser Mohamed, Salma Hossam, Mahmoud Shawky, Abdelrahman Emad |
| Supervisor | Dr. Yasmine el Sharkawy |
| Version and date | v0.1 – 15 Oct 2026 |
| Planned start / finish | 2 Oct 2026 / 4 Dec 2026 |

# 1. Project Overview and Charter

| Item | Response |
| --- | --- |
| Problem / opportunity | Most engineering and technology graduation projects in Egyptian universities end at the final discussion. They are rarely tested against real market needs, and students lack access to mentors, evaluation tools and investors. |
| Target users | Students at engineering/technology faculties and institutes; mentors (industry and academic experts); investors and funding bodies; platform admins/supervisors. |
| Purpose | Convert graduation projects into viable startups by bridging academia and the industrial, technological and agricultural sectors. |
| SMART objective | By 4 Dec 2026, deliver a working MVP of GradUp (apply, evaluate, mentor-match, track progress, investor showcase) and validate it in a pilot with at least 3 teams, 3 mentors and 2 investor/industry reviewers, achieving a usability score of at least 75/100 (SUS) and at least 80% of must-have requirements passed. |
| Proposed solution | A bilingual (Arabic/English) web platform with project profiles, application and scoring, mentor matching and session scheduling, milestone tracking dashboard, and an investor showcase. |
| Expected benefits | Expected benefits include a higher rate of graduation projects reaching MVP stage, faster access to mentors, and greater visibility to investors. |
| Success criteria | See SMART objective, plus: all deliverables D1–D5 accepted by the supervisor; zero open critical defects at submission; pilot feedback documented. |
| Constraints / assumptions | Constraints: fixed DEPI deadline; student team time; no paid budget beyond free tiers. Assumptions: pilot teams and mentors will be reachable; one university or institute will allow a pilot; free hosting tiers will be sufficient. |

## SMART check

| Specific | Measurable | Achievable | Relevant | Time-bound |
| --- | --- | --- | --- | --- |
| Working MVP piloted with real users | SUS score, requirement pass rate, pilot counts | MVP scope is limited; pilot is small | Directly serves the DEPI industry objective | 4 Dec 2026 |

# 2. Scope and Requirements

| In scope | Out of scope |
| --- | --- |
| Student/team registration and project profile | Direct payments, funding transfers or equity handling |
| Application form and status workflow | Legal company registration services |
| Evaluation scorecard for mentors/admins | Native mobile apps (responsive web only) |
| Mentor directory, matching and session booking | Students outside Egypt or non-technical faculties |
| Progress dashboard with milestones | AI-based matching (listed as future phase) |
| Investor showcase (approved projects, request contact) | Full NDA e-signature workflow (basic confidentiality notice only) |
| Arabic/English interface with RTL support | Large-scale load and penetration testing |

## Requirements list

| ID | Requirement | Priority | How to verify | Activity (Primavera) | Duration | Start | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- |
| REQ-01 | Users can register and log in with a role (student, mentor, investor, admin). | H | Functional test | A1020 Develop Authentication & Roles | 6 days | 21 Oct 2026 | Asser Mohamed |
| REQ-02 | A team can create a project profile with problem, solution, sector, stage and documents. | H | Functional test | A1030 Develop Project Profiles & Sector Classification | 7 days | 29 Oct 2026 | Asser Mohamed |
| REQ-03 | A team can submit an application and see its status (submitted, under review, accepted, rejected, needs changes). | H | Functional test | A1040 Develop Reviewer Screening Queue | 5 days | 09 Nov 2026 | Asser Mohamed |
| REQ-04 | Mentors/admins can score a project using the agreed criteria and leave comments. | H | Test + review with supervisor | A1040 Develop Reviewer Screening Queue | 5 days | 09 Nov 2026 | Asser Mohamed |
| REQ-05 | A team can request a mentor and book a session; the mentor can accept or decline. | H | Functional test | A1050 Develop Mentorship & Business Model Canvas | 6 days | 09 Nov 2026 | Asser Mohamed |
| REQ-06 | Each project has a milestone tracker showing stage and completed tasks. | H | Functional test | A1050 Develop Mentorship & Business Model Canvas | 6 days | 09 Nov 2026 | Asser Mohamed |
| REQ-07 | Investors can browse only approved projects and send a contact request. | M | Test + access-control check | A1060 Develop Pitch Board & Investor Requests | 6 days | 17 Nov 2026 | Asser Mohamed |
| REQ-08 | The interface works in Arabic (RTL) and English and on mobile screens. | M | Review on 3 devices | A1010 UI/UX Design & System Architecture | 8 days | 09 Oct 2026 | Salma Hossam |
| REQ-09 | Project data is visible only to authorised roles. | H | Access-control tests | A1080 NFR Performance, Security & QA Testing | 3 days | 01 Dec 2026 | Mahmoud Shawky |
| REQ-10 | Admins see basic reports (projects by sector/stage, sessions held). | L | Review | A1070 Develop Notifications & Admin Console | 4 days | 25 Nov 2026 | Asser Mohamed |

Activity, duration and start date come from the Primavera P6 schedule (data date 16 Oct 2026). A1110 University & Faculty Identity Verification (5 days, 09 Oct 2026) also supports REQ-01 and REQ-09.

Scope control: a new idea is logged as a change request (Section 12) and is not added until approved.

# 3. Deliverables and Acceptance Criteria

| ID / name | Owner | Due | Acceptance criteria / evidence | Approver |
| --- | --- | --- | --- | --- |
| D1: Research and requirements report | Asser Mohamed (research/requirements); Abdelrahman Emad (report documentation) | 8 Oct 2026 | At least 15 student/mentor/investor responses analysed; three existing solutions compared; REQ list approved | Supervisor |
| D2: UX design and system architecture | Salma Hossam / Asser Mohamed | 20 Oct 2026 | Clickable prototype reviewed by 5 users; architecture and data model documented | Supervisor |
| D3: GradUp MVP (working platform) | Asser Mohamed | 30 Nov 2026 | All H-priority requirements implemented and demoed | Supervisor |
| D4: Test and pilot report | Mahmoud Shawky | 3 Dec 2026 | Test records for all H-priority requirements; pilot findings and SUS score documented. | Supervisor |
| D5: Final report and presentation | Abdelrahman Emad (report/documentation); Mohamed Rizk, Asser Mohamed and Salma Hossam (presentation/finalization contribution) | 4 Dec 2026 | Follows the submission checklist (Section 17); references and AI-use disclosure included | Supervisor |

Deliverable accountability: Mohamed Rizk (Team Leader) coordinates and tracks all deliverables. The named owner is responsible for preparing the output; contributors may support specific parts. Dr. Yasmine el Sharkawy reviews and approves deliverables as supervisor. Record acceptance evidence and actual pilot results when available; do not report targets as achieved until verified.

# 4. Work Breakdown Structure

| WBS / Activity | Work package | Output | Owner | Effort (duration) |
| --- | --- | --- | --- | --- |
| 2 | GradUp (total project) | MVP launched | Mohamed Rizk | 46 days |
| 2.1 | PROJECT MANAGEMENT & INITIATION | D1 | Mohamed Rizk | 5 days |
| A1000 | Project Initiation & Requirements Gathering | D1 requirements report | Mohamed Rizk, Abdelrahman Emad | 5 days |
| 2.2 | REQUIREMENTS & SYSTEM DESIGN | D2 | Salma Hossam | 8 days |
| A1010 | UI/UX Design & System Architecture | D2 prototype, architecture | Salma Hossam, Asser Mohamed | 8 days |
| A1110 | University & Faculty Identity Verification | Verification flow design | Asser Mohamed | 5 days |
| 2.3 | MVP DEVELOPMENT | D3 | Asser Mohamed + team | 29 days |
| A1020 | Develop Authentication & Roles | Working module | Asser Mohamed | 6 days |
| A1030 | Develop Project Profiles & Sector Classification | Working module | Asser Mohamed | 7 days |
| A1040 | Develop Reviewer Screening Queue | Working module | Asser Mohamed | 5 days |
| A1050 | Develop Mentorship & Business Model Canvas | Working module | Asser Mohamed | 6 days |
| A1060 | Develop Pitch Board & Investor Requests | Working module | Asser Mohamed | 6 days |
| A1070 | Develop Notifications & Admin Console | Working module | Asser Mohamed | 4 days |
| 2.4 | TESTING & QUALITY ASSURANCE | D4 | Mahmoud Shawky | 3 days |
| A1080 | NFR Performance, Security & QA Testing | D4 test report | Mahmoud Shawky | 3 days |
| 2.5 | DEPLOYMENT & LAUNCH | Live MVP | Mohamed Rizk | 1 day |
| A1090 | MVP Deployment & Official Launch | Live MVP | Asser Mohamed, Abdelrahman Emad | 1 day |

# 5. Schedule and Milestones

| Activity | Depends on | Duration | Start | Finish | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- |
| A1000 Project Initiation & Requirements Gathering | -- | 5 days | 02 Oct 2026 | 08 Oct 2026 | Mohamed Rizk, Abdelrahman Emad | Not started |
| A1010 UI/UX Design & System Architecture | A1000 | 8 days | 09 Oct 2026 | 20 Oct 2026 | Salma Hossam, Asser Mohamed | Not started |
| A1110 University & Faculty Identity Verification | A1000 | 5 days | 09 Oct 2026 | 15 Oct 2026 | Asser Mohamed | Not started |
| A1020 Develop Authentication & Roles | A1010 | 6 days | 21 Oct 2026 | 28 Oct 2026 | Asser Mohamed | Not started |
| A1030 Develop Project Profiles & Sector Classification | A1020 | 7 days | 29 Oct 2026 | 06 Nov 2026 | Asser Mohamed | Not started |
| A1040 Develop Reviewer Screening Queue | A1030 | 5 days | 09 Nov 2026 | 13 Nov 2026 | Asser Mohamed | Not started |
| A1050 Develop Mentorship & Business Model Canvas | A1030 | 6 days | 09 Nov 2026 | 16 Nov 2026 | Asser Mohamed | Not started |
| A1060 Develop Pitch Board & Investor Requests | A1050 | 6 days | 17 Nov 2026 | 24 Nov 2026 | Asser Mohamed | Not started |
| A1070 Develop Notifications & Admin Console | A1060 | 4 days | 25 Nov 2026 | 30 Nov 2026 | Asser Mohamed | Not started |
| A1080 NFR Performance, Security & QA Testing | A1070 | 3 days | 01 Dec 2026 | 03 Dec 2026 | Mahmoud Shawky | Not started |
| A1090 MVP Deployment & Official Launch | A1080 | 1 day | 04 Dec 2026 | 04 Dec 2026 | Asser Mohamed, Abdelrahman Emad | Not started |

Dates and durations are taken from the Primavera P6 schedule (critical path: A1000, A1010, A1020 to A1030, A1050, A1060, A1070, A1080, A1090; A1040 has 1 day of float and A1110 has 36 days). Status labels: Not started, In progress, At risk, Blocked, Complete, Accepted.

# 6. Team Structure and Responsibilities

| Role | Responsibilities | Person / backup |
| --- | --- | --- |
| Project manager / team lead | Overall planning and scope coordination; team communication and meetings; progress escalation and tracking of deliverables | Mohamed Rizk / Salma Hossam |
| Research and requirements coordination | Research on user needs and collection/organization of requirements | Asser Mohamed / Mohamed Rizk |
| Schedule and task tracking | Track milestones, task progress, deadlines and schedule updates | Salma Hossam / Mohamed Rizk |
| Risk and issue tracking | Identify, document and follow up risks, blockers and issues; escalate when needed | Mahmoud Shawky / Mohamed Rizk |
| Documentation and report coordination | Organize project documents, maintain report structure, references and versions | Abdelrahman Emad / Salma Hossam |
| Final report / presentation coordination | Coordinate final presentation and submission preparation with the contributing team members | Mohamed Rizk; contributors: Asser Mohamed and Salma Hossam; documentation: Abdelrahman Emad |

## RACI

| Activity | Mohamed Rizk (Lead) | Asser Mohamed | Salma Hossam | Mahmoud Shawky | Abdelrahman Emad | Supervisor |
| --- | --- | --- | --- | --- | --- | --- |
| Draft project plan, objectives and scope | A/R | C | R | I | I | C |
| Research user needs and gather requirements | A | R | C | I | C | I |
| Track schedule, tasks and deadlines | A | I | R | I | I | I |
| Track risks, blockers and issues | A | C | C | R | I | I |
| Organize documentation and reports | A | C | C | I | R | I |
| Team communication and meetings | A/R | C | C | C | C | I |
| Prepare final report and presentation | A | R | R | I | R | C |
| Track deliverables and report progress | A/R | C | R | C | R | I |
| Approve scope changes | R | C | C | C | C | A |
| Accept final project | R | C | C | C | C | A |

R = Responsible (does the work), A = Accountable (one person per activity, final say), C = Consulted, I = Informed. This RACI focuses on project-management responsibilities and reported team contributions; technical work packages remain in the WBS and schedule.

# 7. Communication and Meeting Plan

| Communication | Audience | Frequency | Channel | Owner / record |
| --- | --- | --- | --- | --- |
| Team check-in | Team | Weekly (15 min stand-up twice weekly in build phase) | Team meeting / agreed team chat | Team lead; action log |
| Supervisor update | Supervisor | Every 2 weeks | Email / meeting | Team lead; status report |
| Milestone review | Team + supervisor + sample users | At each milestone | Review session | Deliverable owner; decisions |
| Urgent escalation | Owner + supervisor | Within 24 hours of a critical blocker | Agreed team channel | Person raising it; issue log |

Meeting rules: agenda shared beforehand; every meeting ends with decisions and actions, each with an owner and due date; absent members send an update and read the notes.

# 8. Risk Management

Score = probability (1–5) x impact (1–5). Scores of 12 or more need an active response.

| ID / risk | P | I | Score | Response / mitigation | Owner / trigger |
| --- | --- | --- | --- | --- | --- |
| R1: Scope creep (investor payments, AI matching, mobile app) | 4 | 4 | 16 | Change control; lock must-have list; park extras in a Phase 2 backlog | Mohamed Rizk; new request without CR |
| R2: Few mentors/investors respond for interviews and pilot | 4 | 4 | 16 | Start outreach in week 1 via DEPI, supervisor and LinkedIn; target 2x the needed number; fall back to academic mentors | Abdelrahman Emad; fewer than 50% replies by 14 Oct |
| R3: Pilot users not available | 3 | 4 | 12 | Agree on one university/institute early; use supervisor channel; simulate with role-play only as a documented fallback | Mohamed Rizk; no pilot confirmation by 20 Oct |
| R4: Team member delay or absence | 3 | 3 | 9 | Interim deadlines; pair on critical modules; named backups | Mohamed Rizk; missed checkpoint |
| R5: Data privacy and IP concerns of students | 3 | 4 | 12 | Role-based access, confidentiality notice, collect minimum data, no real sensitive data in demos | Asser Mohamed; access-control test fails |
| R6: Technical underestimation (matching, dashboards) | 3 | 4 | 12 | Build the simplest version first; weekly demo; cut L-priority requirements before H | Asser Mohamed; module over 20% late |
| R7: Free hosting limits or downtime | 2 | 3 | 6 | Keep deployment scripts; take regular backups; choose a fallback host | Asser Mohamed; outage |

# 9. Issue, Assumption, Dependency and Decision Logs

| ID / date | Item and impact | Owner | Next action / due | Status |
| --- | --- | --- | --- | --- |
| A-01 / 15 Oct | Assumption: at least 3 mentors will join the pilot. Validate by 16 Oct. | Abdelrahman Emad | Confirm mentors | Open |
| A-02 / 15 Oct | Assumption: one institute will host the pilot. Validate by 20 Oct. | Mohamed Rizk | Contact supervisor/DEPI | Open |
| DEP-01 / 15 Oct | Dependency: testing depends on MVP completion on 30 Nov 2026. | Mahmoud Shawky | Prepare test cases earlier | Open |
| DEC-01 / 15 Oct | Decision: MVP is a responsive web app, bilingual, no payment handling (reason: time and risk). | Mohamed Rizk | Record approval from supervisor | Pending approval |

# 10. Quality Management and Testing

| Area | Planned check | Evidence / threshold | Owner |
| --- | --- | --- | --- |
| Accuracy | Verify market claims and sources in the report | All key claims referenced | Abdelrahman Emad |
| Completeness | Trace each requirement to a test | 100% of H requirements tested | Mahmoud Shawky |
| Usability / user fit | Prototype and pilot sessions with representative users | At least 8 users; SUS score of at least 75 | Salma Hossam |
| Technical performance | Functional, role-access and responsive tests; basic speed check | No critical defects open; main pages load in under 3 seconds on normal connection | Mahmoud Shawky |
| Language / RTL quality | Review all screens in Arabic and English | No broken layouts on 3 devices | Salma Hossam |
| Document quality | Proofread, citations, naming and version check | Final checklist completed | Abdelrahman Emad |

## Test record (examples)

| Test ID | Requirement | Method | Result / evidence | Action / owner |
| --- | --- | --- | --- | --- |
| T-01 | REQ-03 | Submit application and change status as admin | To be recorded during testing | To be assigned if needed |
| T-02 | REQ-09 | Student tries to open another team’s project | To be recorded during testing | To be assigned if needed |
| T-03 | REQ-08 | Open all pages in RTL on phone | To be recorded during testing | To be assigned if needed |

# 11. Resource and Budget Management

Budget target: near-zero cash cost using free tiers and student licences.

| Item | Qty | Estimated cost (EGP) | Actual | Source / owner |
| --- | --- | --- | --- | --- |
| Hosting and database (free tier) | 1 | 0 | TBD | Asser Mohamed |
| Domain name (optional) | 1 | 400 | TBD | Mohamed Rizk |
| Design and project tools (free plans) | 1 | 0 | TBD | Salma Hossam |
| Survey and meeting tools | 1 | 0 | TBD | Abdelrahman Emad |
| Printing, travel to pilot site | TBD | 500 | TBD | Mohamed Rizk |
| Contingency (about 10%) | – | 100 | TBD | Supervisor |
| Total |  | 1,000 | TBD |  |

Non-cash resources: mentor and supervisor time, pilot university access, team hours (about 8–10 hours per member per week). Do not spend or purchase without approval.

# 12. Change Control

| Change ID / date | Requested change / reason | Impact assessment | Decision / approver | Date / status | Plan / log updated |
| --- | --- | --- | --- | --- | --- |
| CR-01 / 16 Oct 2026 | Add email notifications when an application status changes, so student teams receive updates without repeatedly checking the platform. | Scope: small enhancement to the existing notification module. Schedule: low-to-medium impact; confirm effort with developer. Cost: no added cost expected using free-tier tools. Quality/risk: improves communication; email delivery and privacy need testing. | Pending supervisor review; project lead: Mohamed Rizk. No implementation before approval. | 16 Oct 2026 / Pending approval | If approved: update requirements, A1070 task details, test cases and risk/issue log. Not updated yet. |
| CR-02 / 16 Oct 2026 | Add post-session mentor feedback/rating to help teams assess mentorship quality and improve future matching; requested as an enhancement beyond the current MVP scope. | Scope: adds a new feature not required for the MVP. Schedule: could affect development/testing before 4 Dec 2026. Cost: no added cost expected. Quality/risk: useful feedback, but may expand scope and require moderation/privacy rules. Lower-risk alternative: collect feedback in the pilot survey. | Deferred for Phase 2 unless supervisor approves and confirms no impact to MVP deadline; approver: Dr. Yasmine el Sharkawy (decision pending). | 16 Oct 2026 / Deferred pending review | Baseline unchanged. If reconsidered, update scope, requirements, schedule and risk log after approval. |

# 13. Document and Information Management

Project Repository: https://github.com/Eng-mohamedrizk/DEPI_PEOJECT.git

| Rule | What the team does |
| --- | --- |
| Folder structure | 01_Charter; 02_Planning; 03_Research; 04_Delivery; 05_Testing; 06_Reports; 07_Meetings_and_Logs; 08_Final_Submission |
| File naming | YYYY-MM-DD_GradUp_DocumentName_vX.X (e.g., 2026-10-20_GradUp_RiskRegister_v1.0) |
| Versioning | v0.1 drafts; v1.0 first approved; v1.1 minor edits; v2.0 major revision |
| Source code | Git repository with protected main branch; code reviewed before merge |
| Access and privacy | Authorised members only; no personal or confidential project data in public folders |
| Backups | Shared drive plus Git; weekly database backup during pilot |
| References | Cite sources in the style required by DEPI |

## Document register

| Document | Owner | Version | Approval | Location |
| --- | --- | --- | --- | --- |
| Project charter | Mohamed Rizk | v0.1 | Pending | Pending |
| Project management plan | Mohamed Rizk | v0.1 | Pending | Pending |
| Schedule and WBS | Mohamed Rizk | v0.1 | Pending | Pending |
| Risk and issue logs | Mohamed Rizk | v0.1 | Pending | Pending |
| Final report / presentation | Abdelrahman Emad | – | – | Pending |

# 14. Progress Monitoring and Reporting

A status report is sent every 2 weeks using this format:

| Field | Team update |
| --- | --- |
| Reporting period | To be completed |
| Overall status | Green / Amber / Red |
| Completed this period | To be completed |
| Next period priorities | To be completed |
| Schedule / budget variance | To be completed |
| Top risks / issues | To be completed |
| Decisions / support needed | To be completed |

Tracking measures: percentage of requirements built and tested, milestones on time, open defects by severity, and risk scores. Escalate early: if a milestone is likely to be missed, tell the supervisor immediately with impact, options and the decision needed.

# 15. Stakeholder and User Engagement

| Stakeholder | Interest / influence | What they need | Engagement | Owner |
| --- | --- | --- | --- | --- |
| Students / graduation teams | High / medium | Easy application, feedback, mentor access | Survey, prototype tests, pilot | Abdelrahman Emad |
| Mentors | High / high | Clear time commitment, simple scheduling | Interviews, pilot feedback | Abdelrahman Emad |
| Investors / industry partners | Medium / high | Quality projects, clear business case | Interviews, showcase demo | Mohamed Rizk |
| Supervisor / DEPI | High / high | Progress, quality, approvals | Bi-weekly update, milestone reviews | Mohamed Rizk |
| University / institute partner | Medium / high | Student benefit, low admin burden | Introductory meeting, pilot agreement | Mohamed Rizk |

# 16. Ethics, Data and Responsible Practice

- Get consent before interviews or surveys and explain how responses will be used.

- Collect only needed data; use test or anonymised data in demos.

- Respect students’ intellectual property: investors see only approved projects and only the information the team agreed to share.

- Store data securely, restrict access, and do not publish real participant data.

- Clearly distinguish assumptions, expected benefits and verified pilot results; document pilot limitations.

- Cite all sources, images and libraries and respect licences.

- If AI tools are used, verify outputs, protect confidential information, disclose use as DEPI requires, and keep the team responsible for the final work.

# 17. Final Report and Presentation Checklist

- ☐ Problem, target users and objective are clear.

- ☐ Solution is supported by research evidence.

- ☐ Scope, deliverables, requirements and acceptance criteria are documented.

- ☐ Schedule, roles, resources and key decisions are summarised.

- ☐ Testing and pilot results, including limitations, are documented.

- ☐ Risks, issues and changes are explained.

- ☐ Impact is measured against the success criteria.

- ☐ References, appendices and AI-use disclosure follow the rules.

- ☐ Files are correctly named and stored in the agreed location.

- ☐ Supervisor has received everything by 4 Dec 2026.

# 18. Project Closure and Lessons Learned

| Closure item | Evidence / response | Owner / date |
| --- | --- | --- |
| Final deliverables accepted | To be recorded at closure | TBD |
| Outstanding items and limitations | To be recorded at closure | TBD |
| Handover / next steps | To be confirmed | TBD |
| Files and access handed over | To be recorded at handover | TBD |
| Budget reconciled | To be reconciled at closure | TBD |
| Lessons learned | To be recorded at closure | TBD |

# 19. Weekly Team Action Tracker

| Week / date | Action | Owner | Due | Priority | Status / evidence |
| --- | --- | --- | --- | --- | --- |
| Week 1 (1 Oct) | Finalise charter and send to supervisor | Mohamed Rizk | 6 Oct | H | Evidence link to be added |
| Week 1 | Create shared folder, Git repo and task board | Abdelrahman Emad | 4 Oct | H | Evidence link to be added |
| Week 1 | Draft interview and survey questions | Abdelrahman Emad | 6 Oct | H | Evidence link to be added |
| Week 2 (5 Oct) | Send outreach to 10 mentors and 6 investors/industry contacts | Abdelrahman Emad | 8 Oct | H | Evidence link to be added |
| Week 2 | Confirm pilot institute with supervisor | Mohamed Rizk | 12 Oct | M | Evidence link to be added |

# 20. Approval and Commitment

| Role | Name | Signature / confirmation | Date |
| --- | --- | --- | --- |
| Project manager / team lead | Mohamed Rizk (Team leader) | Pending | Pending |
| Team representative | Dr. Yasmine el Sharkawy | Pending | Pending |
| Supervisor / assessor | Dr. Yasmine el Sharkawy | Pending | Pending |

# Appendix A – Submission Package

Project charter; project management plan; evidence folder (research, minutes, tests, prototype, approvals); final report; presentation and live demo (problem, evidence, solution, validation, impact, next steps); closure record.

# Appendix B – One-Page Snapshot

| Field | Snapshot |
| --- | --- |
| Project / team | GradUp / Mohamed Rizk (Team leader), Asser Mohamed, Salma Hossam, Mahmoud Shawky, Abdelrahman Emad |
| Problem and user | Graduation projects rarely become startups; students lack mentors, evaluation and investor access. |
| Objective and measure | Pilot-validated MVP by 4 Dec 2026; SUS of at least 75; at least 80% of must-have requirements passed. |
| Main deliverables | D1 research, D2 design, D3 MVP, D4 test and pilot report, D5 final report |
| Next milestone | Charter approved, 6 Oct 2026 |
| Current status | Green – planning started |
| Top 3 risks | 1. Scope creep 2. Low mentor/investor response 3. No confirmed pilot institute |
| Decision / support needed | Supervisor to approve scope and help secure a pilot institute by 20 Oct |
| Project folder | Repository link to be provided |